## Planning
Planning
Elève | Leon Bergmann | [11 empty] | Classe | 300233
Projet | Remnant 2 Build Planner | [11 empty] | Module |  | 151
| Bloc 1 |  |  | Bloc 2 |  |  | Bloc 3 |  |  | Bloc 4 |  |  | Bloc 5
Tâches | 27.01.2025 - MAT | 27.01.2025 - A-M | 28.01.2025 - MAT | 03.02.2025 - MAT | 03.02.2025 - A-M | 04.02.2025 - MAT | 10.02.2025 - MAT | 10.02.2025 - A-M | 11.02.2025 - MAT | 17.02.2025 - MAT | 17.02.2025 - A-M | 18.02.2025 - MAT | 24.02.2025 - MAT | 24.02.2025 - A-M | 25.02.2025 - MAT
Exercices / découverte | X | X | X
Analyse
Use case |  | X
Maquettes |  | X | X |  | X
activity diagram |  |  | X | X
system sequence diagram |  |  |  | X
ER diagram |  |  | X
Conception
class diagram client |  |  |  |  | X | X
class diagram server | [5 empty] | X
relation schema |  |  |  | X
sequence interaction diagram | [5 empty] | X
test concept | [5 empty] | X
Réalisation
Login Page | [6 empty] | X
Build Planner Page | [6 empty] | X | X
Database | [7 empty] | X | X
add Data to database | [8 empty] | X
Login/Logout system | [7 empty] | X | X
sign up system | [7 empty] | X
load builds | [10 empty] | X
create Build | [11 empty] | X
modify build | [11 empty] | X
delete Build | [11 empty] | X
calculations | [9 empty] | X | X
Tests de l'application

## Journal de travail
Journal de travail - 151
Elève / classe | Leon Bergmann
Projet | Remnant 2 Build Planner
Date | Travail effectué | Temps d'exécution [heures]
2025-01-27 | Finished the Use case diagram | 1
2025-01-27 | Started with the maquettes | 1
2025-01-28 | Finished the maquettes | 1
2025-01-28 | Started with the planning | 1
2025-01-28 | Made the ER Schema | 1
2025-01-28 | Made the Activity Diagram | 1
2025-02-03 | updated the Maquettes | 1
2025-02-03 | updated the activity and sequence diagrams | 1.5
2025-02-03 | made the relation Schema | 1.5
2025-02-03 | made the class diagram for the client | 2
2025-02-03 | started with the class diagram for the server | 2
2025-02-04 | finished the class diagram for the server | 0.5
2025-02-04 | made the sequence interaction diagram | 3
2025-02-04 | made the test concept | 0.5
2025-02-10 | applied some necessary improvements to the class, activity and sequence diagrams | 1
2025-02-10 | created the database | 0.5
2025-02-10 | implemented the signup system | 6.5
2025-02-11 | finished the signup system | 1
2025-02-11 | implemented the login system | 1
2025-02-11 | added the data to the database | 1
17.02.1025 | implemented the function to load most data from the database | 3
17.02.1025 | added the logout option | 1
17.02.1025 | implemented most of the calculations | 3
18.02.1025 | finished the worker for the calculations | 1
18.02.1025 | started implementing the calculations into the application | 1
18.02.1025 | started implementing the function to load builds | 2
2025-02-24 | finished implementing the function to load builds | 3
2025-02-24 | started implementing the function to save builds | 2
2025-02-24 | put a first version of the application onto the webserver | 2
2025-02-24 | fixed multiple bugs with help from the teacher | 1
2025-02-25 | continued the implementation of the function to save builds | 2
2025-02-25 | implemented the function to create new builds | 1
2025-02-25 | implemented the function to delete existing builds | 1
Total |  | 52
A mettre :
· Toutes les tâches effectuées sur le projet
o Les problèmes rencontrés
· Toutes les rencontres avec le professeur
o Ce qui a été contrôlé
o Ce qui a été décidé